## Project Tracking
PROJECT TRACKING | [6 empty] | Smartsheet Tip ➜ | Customize the list of possible statuses and priorities to the right so that the Status and Priority columns can use standardized values. |  |  |  | STATUS KEY | PRIORITY KEY
[12 empty] | On Hold | Low
PROJECT TITLE |  | AI Challenge |  |  |  |  | COMPANY NAME | AWARE@THI |  |  |  | Not Yet Started | Medium
PROJECT MANAGER |  | Team |  |  |  |  | DATE | 2021-04-15 |  |  |  | In Progress | High
Complete
PROJECT DETAILS | [7 empty] | DELIVERABLES
STATUS | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | ESTIMATED HOURS | ACTUAL HOURS
Artificial Intelligence Components | [8 empty] | 45.75% | 55 | 56
On Hold | High | 2018-09-09 | 2018-09-10 | 1 | Task |  | Training and test data |  | 100% | 30 | 25
On Hold | High | 2018-09-09 | 2018-09-10 | 1 | Task |  | Object detection and classification |  | 100% | 30 | 25
Not Yet Started | Low | 2018-09-10 | 2018-09-14 | 4 | Task |  | Semantic segmentation |  | 50% | 11 | 10
In Progress | Medium | 2018-09-11 | 2018-09-20 | 9 | Task |  | Sensor set selection & Sensor fusion |  | 22% | 12 | 18
Complete | Medium | 2018-09-12 | 2018-09-20 | 8 | Task |  | Speech recognition and transformation into control commands |  | 11% | 2 | 3
Complete | Medium | 2018-09-12 | 2018-09-20 | 8 | Task |  | Matching of spoken words to detected objects |  | 11% | 2 | 3
Testing in Airsim | [8 empty] | 2.75% | 33 | 32
On Hold | High | 2018-09-09 | 2018-09-10 | 1 | Task |  | Details of task here |  | 11% | 20 | 20
Not Yet Started | Low | 2018-09-10 | 2018-09-14 | 4 | Task |  | Details of task here |  | 0% | 6 | 5
In Progress | Medium | 2018-09-11 | 2018-09-20 | 9 | Task |  | Details of task here |  | 0% | 5 | 5
Complete | Medium | 2018-09-12 | 2018-09-20 | 8 | Task |  | Details of task here |  | 0% | 2 | 2
Virtual to Real | [8 empty] | 2.75% | 33 | 32
On Hold | High | 2018-09-09 | 2018-09-10 | 1 | Task |  | Details of task here |  | 11% | 20 | 20
Not Yet Started | Low | 2018-09-10 | 2018-09-14 | 4 | Task |  | Details of task here |  | 0% | 6 | 5
In Progress | Medium | 2018-09-11 | 2018-09-20 | 9 | Task |  | Details of task here |  | 0% | 5 | 5
Complete | Medium | 2018-09-12 | 2018-09-20 | 8 | Task |  | Details of task here |  | 0% | 2 | 2